## UI
기본 설계 1차 | 3/10 버전 |  | 사내UI표준
http://uidev.sdsdevplatform.io/portal/#/catalog/Vue/About/Vue
개발순서
|  | 1 | router 구성
|  | 2 | 각 화면 template구성
|  | 3 | 데이터 연계 설계
|  | 4 | 각 화면 Component 구성
2안 | 03/30 버전
* 비교페이지 - 시간대
* 메인페이지 변경
* 룰 적용
|  |  |  | * 기존 프로젝트 저장 | => | 불러오기 | 테이블 별도 생성
* 프로젝트별 테이블 생성?
전체 App.vue
GNB.vue
Search.vue
Statisctics.vue
Gridtable.vue
Init.vue - Modal
Analysis.vue
Main.vue
Graph.vue
Notice.vue / Warning 영역

## UI_0401피드백
개발순서
router 구성 |  | TODO
각 화면 template구성 |  | 1. 공통 CSS 파일 별도로 만들고 link 형태로 만들 것
데이터 연계 설계 |  | 2. layout 하위에 종류별 folder 생성할 것 - 예 : chart_bar, chart_line 그리고 Data를 재사용할 수 있도록
각 화면 Component 구성
3안 | 04/01 버전
변경사항
|  |  | * 비교페이지 - 시간대 |  | 별도 페이지 작성필요
* 메인페이지 변경
|  |  | * 룰 적용 | 만들기부터
|  |  | * 기존 프로젝트 저장 |  | => | 불러오기 | 테이블 별도 생성
Compare.vue
Analysis.vue촘ㄳ
전체 App.vue
Search.vue
Statisctics.vue
Gridtable.vue
Init.vue - Modal (불러오기 필요)
Graph-모양.vue
GNB.vue
* 로그 분석관련 기본정보
- 사이트명(프로젝트명), 시간, 선택정보(파일포맷, 파일명 등)
* 특이사항(Warning or Suspect)
- 사이트명(프로젝트명), 시간, 선택정보(파일포맷, 파일명 등)
Notice.vue / Warning 영역
Info.vue
Search.vue
Search.vue
Detail.vue
Search.vue
Graph-모양.vue
GNB.vue
GNB.vue
무엇이 이상한지 한눈에 볼 수 있도록 ... 만들자
Async 처리

## UI_Initialization
|  |  | STEP1 | STEP2 | STEP3
|  |  | 기존 Project 로딩 | 추가 가능 |  | 현재 Session관련
|  |  | 신규 Project 생성 | 로그파일 선택 | 로그포맷 설정 | 상태 보여주기
로딩 데이터범위 설정
- 전체 '- From일시 ~ To일시
|  | 기본 화면 | 현재 정보
Step1
|  |  | Project | New | Exist
|  | New | project_name
project_description
[5 empty] | Cancel | Next(Step2)
|  | Exist | project_name | project_description | uploader | created
|  |  | ROW 선택 후 OK : Loading |  |  |  | Vuex - State
[7 empty] | 검색정보 | fromDate | YYYYMMDD
[5 empty] | OK | Add(Step2) |  | toDate | YYYYMMDD
[8 empty] | fromTime | HHMMSS
|  | Step2 | [5 empty] | toTime | HHMMSS
|  |  | file | 버튼 | file size (자동계산) |  |  | fromTimeTaken
|  |  | file format | DropBox |  |  |  | toTimeTaken
|  |  |  | 기본선택 |  |  |  | condition | I, R, E, U, S (위 1~5)
|  |  |  | Custom |  |  |  | searchKeyword | 검색문자열
|  |  | data range | 전체 |  |  | 공통정보 | projectName
|  |  |  | From 일시~ To 일시 |  |  |  | fileNames
| file upload부분 |  |  |  | Prev(Step1) | Next(Step3) |  | logFormat
1 | Single File
2 | Multi File | Step3 | 최종확인
2 | Editable |  | New/Exist
https://serversideup.net/uploading-files-vuejs-axios/ |  |  | project_name
project_description
file
file format
data range
[5 empty] | Prev(Step2) | OK
Init.vue
click
click
project id 받아야 한다.
logmaster 생성
logfile 생성
logdetail 생성
logmaster 생성
click
click

## UI_Detail
[10 empty] | Date | 연,월,일,시, 분, 초 | 기간별 검색(From, To)
[8 empty] | I | 1 | IP | IP 검색 | Regular Expression 검색
[8 empty] | R | 2 | Request | Request 검색
[8 empty] | E | 3 | Referrer | Referrer 검색
[8 empty] | U | 4 | UserAgent | UserAgent검색
[8 empty] | S | 5 | Status | Http 코드 검색
[10 empty] | TimeTaken | TimeTaken 검색 | 범위 검색(From, To) | 단위 고려 : ms, s
Gridtable | [9 empty] | Vuex - State
[10 empty] | 검색정보 | fromDate | YYYYMMDD
Date | Time | IP | Request | Referrer | UserAgent | Status | TimeTaken |  |  |  | toDate | YYYYMMDD
[11 empty] | fromTime | HHMMSS
[11 empty] | toTime | HHMMSS
fromTimeTaken
toTimeTaken
[11 empty] | condition | I, R, E, U, S (위 1~5)
[11 empty] | searchKeyword | 검색문자열
[10 empty] | 공통정보 | projectName
fileNames
logFormat
Authorization
Log Details - 로그 분석 프로젝트명
Date/Time
Timetaken
Condition
Initialize / Search
TODO : Row 클릭시 상세페이지 로딩필요(로그 전체 확인)

## UI_LogFormat
제품명 조건 로그포맷 조회
수정/추가 버튼 클릭 시 입력 팝업 생성
수정/삭제는 확인 팝업
조회결과 클릭 시 해당 제품 로그포맷 설명 출력
UpdateLogformatForm.vue - Modal
Logformat.vue
LogformatSearch.vue
LogformatResult.vue
LogformatDetail.vue
AddLogformatForm.vue - Modal
수정 시
삭제 시

## ChartJS
버전 | 2.9.3
vue-chartjs
버전 | 3.5.0 | chart 성능
chart 데이터 이동은 props를 이용한다. |  |  | (예시;)
<bar-chart :data="barChartData" :options="barChartOptions" :height="200" />

## Table
Log Master | [11 empty] | Date | 시, 분, 초 및 기간별 검색
| ID(PK) | projectid | projectname | filename | filepath | fileformat | uploader | created |  |  |  | IP | IP 검색
| 자동채번 | 자동채번 | 프로잭트 명 | 파일명 | 저장위치 | 로그포맷 | 요청자 | 생성일시 |  |  |  | Referrer | Referrer검색
| UUIDField |  | CharField | FileField | FilePathField | CharField | CharField | DateTimeField |  |  |  | UserAgent | UserAgent검색
postgresql 타입 | [11 empty] | Status | Http 코드 검색
[12 empty] | TimeTaken | TimeTaken 검색
Log Detail |  |  |  | Paging용 | 필터용 필드
| ID | projectid(FK) | logcontent | line | fhour | fminute | fsecond | fip | freferrer | fuseragent | fstatus | ftimetaken | reserve1 | reserve2 | reserve3 | created
| 자동채번 | 자동채번 | 로그 1 line | 로그순서 | 시 | 분 | 초 | IP | freferrer | fuseragent | fstatus | ftimetaken | 예약 필터필드 | 예약 필터필드 | 예약 필터필드 | 생성일시
postgresql 타입 | UUIDField |  | CharField | PositiveIntegerField | CharField | CharField | CharField | CharField | CharField | CharField | CharField | CharField | CharField | CharField | CharField | DateTimeField
[5 empty] | PositiveSmallIntegerField | PositiveSmallIntegerField | PositiveSmallIntegerField |  |  |  |  | PositiveSmallIntegerField
추가 테이블
django model | https://docs.djangoproject.com/en/3.0/ref/models/fields/ | [5 empty] | http://www.cdrf.co/3.1/rest_framework.viewsets/ModelViewSet.html#get_queryset
AutoField
UUIDField
CharField
PositiveIntegerField
DateField
DateTimeField
EmailField
FileField | def user_directory_path(instance, filename): # file will be uploaded to MEDIA_ROOT/user_<id>/<filename> return 'user_{0}/{1}'.format(instance.user.id, filename) class MyModel(models.Model): upload = models.FileField(upload_to=user_directory_path)
FilePathField | FilePathField(path="/home/images", match="foo.*", recursive=True)
ForeignKey | class Car(models.Model): manufacturer = models.ForeignKey( 'Manufacturer', on_delete=models.CASCADE, ) # ... class Manufacturer(models.Model): # ... Pass

## Table_0408
logmaster
| project_id(PK) | project_name | project_description | file_format | uploader | created
| 자동채번 | 프로잭트 명 | 프로잭트 설명 | 로그포맷 | 요청자 | 생성일시
| UUIDField | CharField | TextField | CharField | CharField | DateTimeField
|  | 50 | 300 | 100 | 50
[11 empty] | Date | 시, 분, 초 및 기간별 검색
logfile | [10 empty] | IP | IP 검색
| logfile_id(PK) | project_id(FK) | filen_name | file_path | file_size | created |  |  |  |  | Request | Request 검색 | 추가
| 자동채번 | 생성시입력 | 파일명 | 저장위치 | 로그크기 | 생성일시 |  |  |  |  | Referrer | Referrer 검색
| UUIDField | UUIDField | CharField | FileField | PositiveIntegerField | DateTimeField |  |  |  |  | UserAgent | UserAgent검색
|  |  | 100 | [7 empty] | Status | Http 코드 검색
[11 empty] | TimeTaken | TimeTaken 검색
logdetail |  |  |  | 필터용 필드
| id(PK) | logfile_id(FK) | log_line | fyear | fmonth | fday | fhour | fminute | fsecond
| 자동채번 | 생성시입력 | 로그 1 line | 시 | 분 | 초 | 시 | 분 | 초
| UUIDField | UUIDField | TextField | PositiveSmallIntegerField | PositiveSmallIntegerField | PositiveSmallIntegerField | PositiveSmallIntegerField | PositiveSmallIntegerField | PositiveSmallIntegerField
1000
필터용 필드
| frequest | fip | freferrer | fuseragent | fstatus | ftimetaken | reserve1 | reserve2 | reserve3 | created
| request | IP | referrer | useragent | status | timetaken | 예약 필터필드 | 예약 필터필드 | 예약 필터필드 | 생성일시
| CharField | CharField | CharField | CharField | CharField | PositiveIntegerField | CharField | CharField | CharField | DateTimeField
| 200 | 40 | 200 | 200 | 10 |  | 200 | 200 | 200
https://httpd.apache.org/docs/2.4/ko/mod/mod_log_config.html#formats
| 형식 문자열 | 설명 |  | 형식 문자열 | 설명 |  | 형식 문자열 | 설명 |  |  | Common Log Format (CLF)
1 | %% | 퍼센트 기호 |  | %...{Foobar}i | 서버가 수신한 요청에서 Foobar: 헤더의 내용. |  | %...t | common log format 시간 형식(표준 영어 형식)의 시간 |  |  | "%h %l %u %t \"%r\" %>s %b"
2 | %...a | 원격 IP-주소 |  | %...l | (있다면 identd가 제공한) 원격 로그인명. mod_ident가 있고 IdentityCheck가 On이 아니면 빼기기호를 기록한다. |  | %...{format}t | strftime(3) 형식 format의 시간. (지역시간일 수 있음) |  |  | 가상호스트 정보를 포함한 Common Log Format
3 | %...A | (서버) IP-주소 |  | %...m | 요청 메써드 |  | %...T | 요청을 처리하는데 걸린 시간 (초 단위). |  |  | "%v %h %l %u %t \"%r\" %>s %b"
4 | %...B | HTTP 헤더를 제외한 전송 바이트수. |  | %...{Foobar}n | 다른 모듈이 기록한 Foobar 노트(note) 내용. |  | %...u | 원격 사용자 (auth가 제공하며, 상태(%s)가 401인 경우 이상한 값을 나올 수 있음) |  |  | NCSA extended/combined 로그 형식
5 | %...b | HTTP 헤더를 제외한 전송 바이트수. CLF 형식과 같이 전송한 내용이 없는 경우 0 대신 '-'가 나온다. |  | %...{Foobar}o | 응답의 Foobar: 헤더 내용. |  | %...U | 질의문자열을 제외한 요청 URL 경로. |  |  | "%h %l %u %t \"%r\" %>s %b \"%{Referer}i\" \"%{User-agent}i\""
6 | %...{Foobar}C | 서버가 수신한 요청에서 Foobar 쿠키의 내용. |  | %...p | 요청을 서비스하는 서버의 정규 포트 |  | %...v | 요청을 서비스한 서버의 정규 ServerName. |  |  | Referer 로그 형식
7 | %...D | 요청을 처리하는데 걸린 시간 (마이크로초 단위). |  | %...P | 요청을 서비스하는 자식의 프로세스 ID. |  | %...V | UseCanonicalName 설정에 따른 서버명. |  |  | "%{Referer}i -> %U"
8 | %...{FOOBAR}e | 환경변수 FOOBAR의 내용 |  | %...{format}P | 요청을 서비스하는 자식의 프로세스 ID 혹은 쓰레드 ID. format에는 pid와 tid가 가능하다. |  | %...X | 응답을 마쳤을때 연결 상태. |  |  | Agent (브라우저) 로그 형식
9 | %...f | 파일명 |  | %...q | 질의문자열 (질의문자열이 있다면 앞에 ?를 붙이고, 없다면 빈 문자열) |  |  | X = | 응답을 마치기 전에 연결이 끊어졌다. |  | "%{User-agent}i"
10 | %...h | 원격 호스트 |  | %...r | 요청의 첫번째 줄 |  |  | + = | 응답을 보낸후에도 연결이 살아있다(keep alive).
11 | %...H | 요청 프로토콜 |  | %...s | 상태(status). 내부 리다이렉션된 요청의 경우 *원래* 요청의 상태이다. 최종 요청의 상태는 %...>s. |  |  | - = | 응답을 보낸후 연결이 끊어졌다.
12 | %...O | 헤더를 포함한 송신 바이트수로 0일 수 없다. 이를 사용하려면 mod_logio가 필요하다. |  | %...I | 요청과 헤더를 포함한 수신 바이트수로 0일 수 없다. 이를 사용하려면 mod_logio가 필요하다. |  |  | (아파치 1.3 후반 버전에서 이 지시어는 %...c였지만, 전통적인 ssl %...{var}c 문법과 겹쳐서 변경했다.)

## Table_0619_0429
logmaster
| project_id(PK) | project_name | project_description | file_format | creator | created
| 자동채번 | 프로잭트 명 | 프로젝트 설명 | 로그포맷 | 요청자 | 생성일시
| UUIDField | CharField | TextField | CharField | CharField | DateTimeField
|  | 50 | 300 | 100 | 50 | [5 empty] | Date | 시, 분, 초 및 기간별 검색
[11 empty] | IP | IP 검색
logfile |  |  |  |  | file_object | [5 empty] | Request | Request 검색
| logfile_id(PK) | project_id(FK) | filen_name | file_format | file_path | file_size | created |  |  |  | Referrer | Referrer 검색 | 추가
| 자동채번 | 생성시입력 | 파일명 | 로그포맷 | 저장위치 | 로그크기 | 생성일시 |  |  |  | UserAgent | UserAgent검색
| UUIDField | UUIDField | CharField | CharField | FileField | PositiveIntegerField | DateTimeField |  |  |  | Status | Http 코드 검색
|  |  | 100 | 100 | [6 empty] | TimeTaken | TimeTaken 검색
logdetail |  |  |  | 필터용 필드
| id(PK) | logfile_id(FK) | log_line | fyear | fmonth | fday | fhour | fminute | fsecond | fdate | ftime | fdatetime
| 자동채번 | 생성시입력 | 로그 1 line | 연 | 월 | 일 | 시 | 분 | 초 | 날짜 | 시간 | 날짜시간
| UUIDField | UUIDField | TextField | CharField (4) | CharField (2) | CharField (2) | CharField (2) | CharField (2) | CharField (2) | CharField (8) | CharField (6) | CharField (14)
|  |  | 1000 | 날짜: YYYYMMDD; 시간: hhmmss; 날짜시간: YYYYMMDDhhmmss
필터용 필드 | bar: 연 to 날짜
| frequest | fip | freferrer | fuseragent | fstatus | ftimetaken | reserve1 | reserve2 | reserve3 | created | project_id(PK) | Multifile 차리위해 들고 있어야 한다.
| request | IP | referrer | useragent | status | timetaken | 예약 필터필드 | 예약 필터필드 | 예약 필터필드 | 생성일시 | 자동채번
| CharField | CharField | CharField | CharField | CharField | PositiveIntegerField | CharField | CharField | CharField | DateTimeField | UUIDField
| 200 | 40 | 200 | 연: 200; 월: 10; 시: 200; 분: 200; 초: 200
https://httpd.apache.org/docs/2.4/ko/mod/mod_log_config.html#formats
| 형식 문자열 | 설명 |  | 연: 형식 문자열; 월: 설명; 시: 형식 문자열; 분: 설명; 시간: Common Log Format (CLF)
1 | %% | 퍼센트 기호 |  | 연: %...{Foobar}i; 월: 서버가 수신한 요청에서 Foobar: 헤더의 내용.; 시: %...t; 분: common log format 시간 형식(표준 영어 형식)의 시간; 시간: "%h %l %u %t \"%r\" %>s %b"
2 | %...a | 원격 IP-주소 |  | 연: %...l; 월: (있다면 identd가 제공한) 원격 로그인명. mod_ident가 있고 IdentityCheck가 On이 아니면 빼기기호를 기록한다.; 시: %...{format}t; 분: strftime(3) 형식 format의 시간. (지역시간일 수 있음); 시간: 가상호스트 정보를 포함한 Common Log Format
3 | %...A | (서버) IP-주소 |  | 연: %...m; 월: 요청 메써드; 시: %...T; 분: 요청을 처리하는데 걸린 시간 (초 단위).; 시간: "%v %h %l %u %t \"%r\" %>s %b"
4 | %...B | HTTP 헤더를 제외한 전송 바이트수. |  | 연: %...{Foobar}n; 월: 다른 모듈이 기록한 Foobar 노트(note) 내용.; 시: %...u; 분: 원격 사용자 (auth가 제공하며, 상태(%s)가 401인 경우 이상한 값을 나올 수 있음); 시간: NCSA extended/combined 로그 형식
5 | %...b | HTTP 헤더를 제외한 전송 바이트수. CLF 형식과 같이 전송한 내용이 없는 경우 0 대신 '-'가 나온다. |  | 연: %...{Foobar}o; 월: 응답의 Foobar: 헤더 내용.; 시: %...U; 분: 질의문자열을 제외한 요청 URL 경로.; 시간: "%h %l %u %t \"%r\" %>s %b \"%{Referer}i\" \"%{User-agent}i\""
6 | %...{Foobar}C | 서버가 수신한 요청에서 Foobar 쿠키의 내용. |  | 연: %...p; 월: 요청을 서비스하는 서버의 정규 포트; 시: %...v; 분: 요청을 서비스한 서버의 정규 ServerName.; 시간: Referer 로그 형식
7 | %...D | 요청을 처리하는데 걸린 시간 (마이크로초 단위). |  | 연: %...P; 월: 요청을 서비스하는 자식의 프로세스 ID.; 시: %...V; 분: UseCanonicalName 설정에 따른 서버명.; 시간: "%{Referer}i -> %U"
8 | %...{FOOBAR}e | 환경변수 FOOBAR의 내용 |  | 연: %...{format}P; 월: 요청을 서비스하는 자식의 프로세스 ID 혹은 쓰레드 ID. format에는 pid와 tid가 가능하다.; 시: %...X; 분: 응답을 마쳤을때 연결 상태.; 시간: Agent (브라우저) 로그 형식
9 | %...f | 파일명 |  | 연: %...q; 월: 질의문자열 (질의문자열이 있다면 앞에 ?를 붙이고, 없다면 빈 문자열); 분: X =; 초: 응답을 마치기 전에 연결이 끊어졌다.; 시간: "%{User-agent}i"
10 | %...h | 원격 호스트 |  | 연: %...r; 월: 요청의 첫번째 줄; 분: + =; 초: 응답을 보낸후에도 연결이 살아있다(keep alive).
11 | %...H | 요청 프로토콜 |  | 연: %...s; 월: 상태(status). 내부 리다이렉션된 요청의 경우 *원래* 요청의 상태이다. 최종 요청의 상태는 %...>s.; 분: - =; 초: 응답을 보낸후 연결이 끊어졌다.
12 | %...O | 헤더를 포함한 송신 바이트수로 0일 수 없다. 이를 사용하려면 mod_logio가 필요하다. |  | 연: %...I; 월: 요청과 헤더를 포함한 수신 바이트수로 0일 수 없다. 이를 사용하려면 mod_logio가 필요하다.; 분: (아파치 1.3 후반 버전에서 이 지시어는 %...c였지만, 전통적인 ssl %...{var}c 문법과 겹쳐서 변경했다.)
Logformat |  |  | default외 custom
| format_id(PK) | fomat_kind | format_name | 연: format_strings; 월: creator; 일: created; 시간: 구분; 날짜시간: 우선순위 | default
| 자동채번 | 로그포맷 구분 | 로그포맷명 | 연: 로그포맷; 월: 생성자; 일: 생성일시; 시간: Apache common (CLF) log format; 날짜시간: 1 | LogFormat "%h %l %u %t \"%r\" %>s %b" common
| UUIDField | CharField | CharField | 연: CharField; 월: CharField; 일: DateTimeField; 시간: Apache combined (XLF/ELF); 날짜시간: 1 | LogFormat "%h %l %u %t \"%r\" %>s %b \"%{Referer}i\" \"%{User-Agent}i\"" combined
|  | 50 | 50 | 연: 500; 월: 50; 시간: IIS (W3C) log format; 날짜시간: 1 | https://docs.microsoft.com/en-us/windows/win32/http/w3c-logging
|  | apache/nginx/iis | CLF (참고용) | 연: %h %l %u %t \"%r\" %>s %b; 시간: nginx log format - log format - 내장 variable 확인 필요; 날짜시간: 1 | log_format main '$remote_addr - $remote_user [$time_local] "$request" ' '$status $body_bytes_sent "$http_referer" ' '"$http_user_agent" "$http_x_forwarded_for"';
Logformat_string |  |  |  | 시간: IIS (NCSA) log format; 날짜시간: 2 | https://docs.microsoft.com/en-us/windows/win32/http/ncsa-logging
| formatstring_id(PK) | format_kind | format_string | 연: format_definition; 월: created; 시간: IIS log format; 날짜시간: 2 | 빈도 적음
| 자동채번 | 로그포맷 구분 | 로그포맷명 | 연: 형식 설명; 월: 생성일시; 시간: personalized log format; 날짜시간: 2
| UUIDField | CharField | CharField | 연: CharField; 월: DateTimeField; 시간: tomcat log format; 날짜시간: 2
|  | 50 | 50 | 연: 500
|  | apache | f | 파일명 | %...f | 시간 포맷 중요 | apache | 2번 인덱싱 필요 | df 사용때문에
|  |  | h | 연: 원격 호스트; 월: %...h
iis
nginx
tomcat
weblogic
custom도 이중 하나임

## Pilot
Pilot-ID | 구분 | 기능 | 내용 | 테스트기간 | 완료여부 | 비고
P-001 | Backend | 파일업로드 | 로그 파일을 업로드하여 라인 단위로 읽는 기능 | 03/12~03/14 | 완료
P-002 | Backend | DB설정 및 입력 | Postgresql 서버 주요 테이블 설계 및 데이터 입력 | ~04/08 | 완료
P-002-01 | Backend | 대용량데이터 처리 성능 | logdetail 테이블에 100만건 이상의 데이터 입력 | ~04/17 | 완료 | 130만건/1분
P-003 | Backend | CRUD | CRUD 기본 셋 | ~04/10 | 완료
P-003-01 | Backend | Searching, Ordering, Paging | Searching, Ordering, Paging 기능 | ~04/24 | 완료
P-003-02 | Backend | Exception 처리 로직 | Exception Handling on API call | ~04/28 | 완료
P-004 | Frontend | 기본화면 | Vue 화면 구성 | ~04/03 | 완료 | git반영
P-004-01 | Frontend | Backend 연계 | axios 라이브러리 구성 및 RestAPI Template 코드 작성 | ~04/28 | 완료
P-005 | Frontend | 상세화면 | Backend 연계 - Paging | ~05/31 | 완료 | 디자인 제외
P-006 | Frontend | 상세화면 | Backend 연계 - Searching | ~05/31 | 완료 | 디자인 제외
P-007 | Frontend | 상세화면 | Backend 연계 - Ordering | ~05/31 | 완료 | 디자인 제외
P-008 | Frontend | 차트화면 | Chart.js 화면 구성 | ~06/26 | 완료 | 디자인 제외
P-009 | Frontend | 상세화면 | Backend 연계 | ~06/26 | 완료 | 디자인 제외
P-010 | Frontend | 화면 디자인 | OPUS UI 표준준수 기본화면 | ~05/31 | 완료
Package 구조
loganalyzer | core
| backend | util
|  | api | logapp
|  |  | analysisapp | statistics
chart
|  |  | commapp | setting
user
authorization
| frontend | util
log
analysis
comm

## 아키텍처
3/10 버전
On Single Container?
Postgresql
In Production?

## 기능요건
구분 | 카테고리 | 기능 Level1 | 기능 Level2 | 기능 Level3 | 기능 Level3 | 기능정의 | 우선순위 | 구현일정 | 0401 피드백 | Value Added 기능대상
LogAnalyzer api | Web Log log | 초기화 POST | 파일업로드 |  | 싱글파일 업로드 | 로그포맷 선택화면 포함 | 1 |  |  | static file 처리시간 지연
[5 empty] | 멀티파일 업로드 | 로그파일 추가 | 2 |  |  | Stuck Thread
[5 empty] | 압축파일 업로드 | 압축 로그파일 지원 | 2
|  |  | 불러오기 |  | 파일 불러오기 | 지난 작업내용 불러오기 | 3 |  | 기능 추가
|  | 조회 GET | 필터링(검색) search |  | Request | Regular Expression | 2
[5 empty] | Date | 시, 분, 초 및 기간별 검색 | 1
[5 empty] | IP | IP 검색 | 1
[5 empty] | Referrer | Referrer검색 | 1
[5 empty] | UserAgent | UserAgent검색 | 1
[5 empty] | Status | Http 코드 검색 | 1
[5 empty] | TimeTaken | TimeTaken 검색 | 1
[5 empty] | Countries | Countries 검색 | 3 |  | GeoIP 여부
[5 empty] | Static Files | Static Files 검색 | 2
|  |  | 정렬 order |  | 필터링 항목별 정렬 | Grid 기능에 포함 | 1 |  |  | 통계 공식 - LogDetail Table |  |  | 기본 조건 충족
|  | 분석 analysis | 통계 테이블(표) statistics GET |  | Total Hits | 전체 처리량 | 1 |  |  | Total Hits | 전체 처리량 | 1 | 전체 건수
[5 empty] | Status Codes | 상태코드 Top5 | 1 |  |  | Top IP Addresses | 최다접속 IP주소 | 1
[5 empty] | Bandwidth | 처리량 Top5 | 1 |  | 용어변경 | Top Requests | 최다접속 사용자 요청 | 1
[5 empty] | Top IP Addresses | 최다접속 IP주소 | 1 |  |  | Top 404 URLs | 최다 404 발생 URL | 1
[5 empty] | Top Requests | 최다접속 사용자 요청 | 1 |  |  | Top Referers | 최다접속 Referers | 2
[5 empty] | Top Countries | 최다접속 국가 | 3 |  | GeoIP 여부 | Status Codes Top5 | 상태코드 Top5 | 1 | 상태코드 Grouping, Count 후 < 5
[5 empty] | Top 404 URLs | 최다 404 발생 URL | 1 |  |  | Requests Top5 | 처리량 Top5 | 1 | Requests Grouping, Count 후 < 5
[5 empty] | Top Referers | 최다접속 Referers | 2 |  |  | Search Terms | URL Query Top5 | 1
[5 empty] | Top User Agents | 최다접속 User Agents | 2 |  |  | Visits Count | 방문수 Top5 | 1
[5 empty] | Country IP Addresses | IP Addresses 국가별 Top5 | 3 |  | GeoIP 여부 | Top User Agents | 최다접속 User Agents | 2
[5 empty] | File Types | 파일타입 Top5 | 2 |  |  | File Types | 파일타입 Top5 | 2
[5 empty] | Search Terms | URL Query Top5 | 1 |  |  | Top Countries | 최다접속 국가 | 3
[5 empty] | Visits Count | 방문수 Top5 | 1 |  |  | Country IP Addresses | IP Addresses 국가별 Top5 | 3
[5 empty] | Custom 통계 생성 | 사용자 통계항목 생성 | 3
|  |  | 그래프 chart GET |  | Line | 통계 항목 중 Line 그래프 | 1 |  |  | 전체 평균 처리시간, 분산
[5 empty] | Pie | 통계 항목 중 Pie 그래프 | 1
[5 empty] | Custom 그래프 생성 | x, y, 그래프 종류 선택 가능 | 3
|  | 기타 | 가이드 guide GET |  | Http Code 설명 | Http Code 항목별 설명 | 1
[5 empty] | 사용가이드 | 솔루션 사용가이드 | 2
| WAS Log | TBD | TBD |  | TBD | 별도필요한가? | TBD
| 공통 기능 comm | 관리 management | 설정관리 setting | 개인화면 설정 | 언어설정 | 언어설정 - KO, EN | 2
[5 empty] | 로그포맷 조회 | 지원로그포맷 조회 | 1
[5 empty] | 로그포맷 추가 | 지원로그포맷 추가 | 1
[5 empty] | 로그포맷 삭제 | 지원로그포맷 삭제 | 1
[5 empty] | 로그포맷 변경 | 지원로그포맷 변경 - Default | 1
[5 empty] | 로그포맷 변경 | 지원로그포맷 변경 - Custom | 2
|  |  | 사용자관리 user |  | 개인정보 조회 | 사용자 정보조회 | 2
[5 empty] | 개인정보 변경 | 사용자 정보변경 | 2
|  |  | 권한관리 authorization |  | 개인권한 조회 | 사용자 권한조회 | 2
[5 empty] | 권한설정 | 사용자 권한설정 | 2

## 비기능요건
구분 | 내용 |  | 환경
NFR-01 | 파싱속도 |  | Windows10, 8core, 16GB, remote postgresql 11 on 아키텍처랩(수원)
NFR-02 | 파일크기
NFR-03 | 사용성 |  | 구분 |  | 의미 | 결과 | 1-1 multi object 인서트
|  |  | NFR-01 | 파싱속도 | 로그파일 라인단위 파싱 후 DB 인서트까지 걸린 시간 | 59.1s / 130만건 (apache common 포맷) | ########################################### sqlite3 기준
전략 |  |  |  |  | 전략 : parsing - pandas 사용, insert - postgresql copy 사용 |  | - 400K(5,000라인): 27s
파싱속도 | Kyoto Cabinet On-Disk B+ Tree | [5 empty] | - 900K(11,257라인):
numpy | 활용가능? | [5 empty] | - 100M(1,350,840라인): 몇시간 단위
pandas | 활용가능? -> 적용 | [5 empty] | ###########################################
정규식 | [6 empty] | 1-2 AUTOCOMMIT false 설정
* 프로젝트별 테이블 생성? | [6 empty] | ########################################### sqlite3 기준
- 400K(5,000라인): 8s
| 고려사항 | 전략 |  |  |  |  | - 900K(11,257라인): 18s
1 | parsing 속도 | multiprocessing, multithread, dataframe |  |  | 세부 Steps : 전체 line 수 세기 -> process 수만큼 병렬처리 -> csv 파일생성 | 8G가능(combined IO 기준 480s) | - 100M(1,350,840라인): 2,335s (39분)
2 | DB insert 속도 | postgresql copy |  |  | 135만라인 기준 20~30s, Linear -> 1350라인 300s 예상 |  | ###########################################
3 | 로그테이블 비대화 | dynamic django model for each log |  |  | 완료 |  | ########################################### postgres11 기준
- 400K(5,000라인): 9s
- 900K(11,257라인): 21s
- 100M(1,350,840라인): 2,676s
###########################################
1-3 postgresql copy 방식
###########################################
pandas 및 copy 사용
- 400K(5,000라인): s
- 900K(11,257라인): s
- 100M(1,350,840라인): 59.1s (완료)
###########################################

## 지원포맷
구분 | 우선순위 | default
Apache common (CLF) log format | 1 | LogFormat "%h %l %u %t \"%r\" %>s %b" common
Apache combined (XLF/ELF) | 1 | LogFormat "%h %l %u %t \"%r\" %>s %b \"%{Referer}i\" \"%{User-Agent}i\"" combined
IIS (W3C) log format | 1 | https://docs.microsoft.com/en-us/windows/win32/http/w3c-logging
nginx log format - log format - 내장 variable 확인 필요 | 1 | log_format main '$remote_addr - $remote_user [$time_local] "$request" ' '$status $body_bytes_sent "$http_referer" ' '"$http_user_agent" "$http_x_forwarded_for"';
IIS (NCSA) log format | 2 | https://docs.microsoft.com/en-us/windows/win32/http/ncsa-logging
IIS log format | 2 | 빈도 적음
personalized log format | 2
tomcat log format | 2

## 로그로맷 항목설명
Product | Format String | Description
apache | a | Client IP address of the request.
apache | {c}a | Underlying peer IP address of the connection.
apache | A | Local IP-address.
apache | B | Size of response in bytes, excluding HTTP headers.
apache | b | Size of response in bytes, excluding HTTP headers. In CLF format, i.e. a '-' rather than a 0 when no bytes are sent.
apache | {VARNAME}C | The contents of cookie VARNAME in the request sent to the server. Only version 0 cookies are fully supported.
apache | D | The time taken to serve the request, in microseconds.
apache | {VARNAME}e | The contents of the environment variable VARNAME.
apache | f | Filename.
apache | h | Remote hostname. Will log the IP address if HostnameLookups is set to Off, which is the default.
apache | {c}h | Like h, but always reports on the hostname of the underlying TCP connection and not any modifications to the remote hostname by modules like mod_remoteip.
apache | H | The request protocol.
apache | {VARNAME}i | The contents of VARNAME: header line(s) in the request sent to the server. Changes made by other modules (e.g. mod_headers) affect this.
apache | k | Number of keepalive requests handled on this connection.
apache | l | Remote logname (from identd, if supplied). This will return a dash unless mod_ident is present and IdentityCheck is set On.
apache | L | The request log ID from the error log (or '-' if nothing has been logged to the error log for this request). Look for the matching error log line to see what request caused what error.
apache | m | The request method.
apache | {VARNAME}n | The contents of note VARNAME from another module.
apache | {VARNAME}o | The contents of VARNAME: header line(s) in the reply.
apache | p | The canonical port of the server serving the request.
apache | {format}p | The canonical port of the server serving the request, or the server's actual port, or the client's actual port. Valid formats are canonical, local, or remote.
apache | P | The process ID of the child that serviced the request.
apache | {format}P | The process ID or thread ID of the child that serviced the request. Valid formats are pid, tid, and hextid. hextid requires APR 1.2.0 or higher.
apache | q | The query string (prepended with a ? if a query string exists, otherwise an empty string).
apache | r | First line of request.
apache | R | The handler generating the response (if any).
apache | s | Status. For requests that have been internally redirected, this is the status of the original request. Use >s for the final status.
apache | t | Time the request was received, in the format [18/Sep/2011:19:18:28 -0400]. The last number indicates the timezone offset from GMT
apache | {format}t | The time, in the form given by format, which should be in an extended strftime(3) format (potentially localized).
apache | T | The time taken to serve the request, in seconds.
apache | {UNIT}T | The time taken to serve the request, in a time unit given by UNIT.
apache | u | Remote user if the request was authenticated. May be bogus if return status (s) is 401 (unauthorized).
apache | U | The URL path requested, not including any query string.
apache | v | The canonical ServerName of the server serving the request.
apache | V | The server name according to the UseCanonicalName setting.
apache | X | Connection status when response is completed:
apache | I | Bytes received, including request and headers. Cannot be zero. You need to enable mod_logio to use this.
apache | O | Bytes sent, including headers. May be zero in rare cases such as when a request is aborted before a response is sent. You need to enable mod_logio to use this.
apache | S | Bytes transferred (received and sent), including request and headers, cannot be zero. This is the combination of I and O. You need to enable mod_logio to use this.
apache | {VARNAME}^ti | The contents of VARNAME: trailer line(s) in the request sent to the server.
apache | {VARNAME}^to | The contents of VARNAME: trailer line(s) in the response sent from the server.
Nginx | remote_user | HTTP Authenticated User. When the user name is not set, this field shows
Nginx | remote_addr | Client IP address of the request.
Nginx | time_local | local time in the Common Log Format
Nginx | request | full original request line
Nginx | status | response status
Nginx | body_bytes_sent | number of bytes sent to a client, not counting the response header
Nginx | http_referer | identifies the address of the URI which is linked to the resource being requested
Nginx | http_user_agent | value of standard User Agent HTTP request field
Nginx | http_x_forwarded_for | identifying the originating IP address of a client
Nginx | bytes_sent | the number of bytes sent to a client
Nginx | connection | connection serial number
Nginx | connection_requests | the current number of requests made through a connection (1.1.18)
Nginx | msec | time in seconds with a milliseconds resolution at the time of the log write
Nginx | pipe | “p” if request was pipelined, “.” otherwise
Nginx | request_length | request length (including request line, header, and request body)
Nginx | request_time | request processing time in seconds with a milliseconds resolution; time elapsed between the first bytes were read from the client and the log write after the last bytes were sent to the client
Nginx | time_iso8601 | local time in the ISO 8601 standard format
Nginx | time_local | local time in the Common Log Format
IIS-W3C | date | The date on which the activity occurred.
IIS-W3C | time | The time, in coordinated universal time (UTC), at which the activity occurred.
IIS-W3C | s-sitename | The Internet service name and instance number that was running on the client.
IIS-W3C | s-computername | The name of the server on which the log file entry was generated.
IIS-W3C | s-ip | The IP address of the server on which the log file entry was generated.
IIS-W3C | cs-method | The requested verb, for example, a GET method.
IIS-W3C | cs-uri-stem | The target of the verb, for example, Default.htm.
IIS-W3C | cs-uri-query | The query, if any, that the client was trying to perform. A Universal Resource Identifier (URI) query is necessary only for dynamic pages.
IIS-W3C | s-port | The server port number that is configured for the service.
IIS-W3C | cs-username | The name of the authenticated user that accessed the server. Anonymous users are indicated by a hyphen.
IIS-W3C | c-ip | The IP address of the client that made the request.
IIS-W3C | cs-version | The HTTP protocol version that the client used.
IIS-W3C | cs(User-Agent) | The browser type that the client used.
IIS-W3C | cs(Cookie) | The content of the cookie sent or received, if any.
IIS-W3C | cs(Referrer) | The site that the user last visited. This site provided a link to the current site.
IIS-W3C | cs-host | The host header name, if any.
IIS-W3C | sc-status | The HTTP status code.
IIS-W3C | sc-substatus | The substatus error code.
IIS-W3C | sc-win32-status | The Windows status code.
IIS-W3C | sc-bytes | The number of bytes sent by the server.
IIS-W3C | cs-bytes | The number of bytes received and processed by the server.
IIS-W3C | time-taken | The length of time that the action took, in milliseconds.
IIS-W3C | streamid | The Stream Id.
IIS-NCSA | Remote host address | The IP address of the client that made the request.
IIS-NCSA | Remote log name | Not used. This value is always a hyphen.
IIS-NCSA | User name | The name of the authenticated user that accessed the server. Anonymous users are indicated by a hyphen. The best practice is for the application always to provide the user name.
IIS-NCSA | Date, time, and Greenwich mean time (GMT) offset | The local date and time at which the activity occurred. The offset from Greenwich mean time is also indicated.
IIS-NCSA | Request and Protocol version | The HTTP protocol version that the client used.
IIS-NCSA | Service status code | The HTTP status code. (A value of 200 indicates that the request completed successfully.)
IIS-NCSA | Bytes sent | The number of bytes sent by the server.
IIS | Client IP address | The IP address of the client that made the request.
IIS | User name | The name of the authenticated user that accessed the server. Anonymous users are indicated by a hyphen. The best practice is for the application always to provide the user name.
IIS | Date | The date on which the activity occurred.
IIS | Time | The local time at which the activity occurred.
IIS | Service and instance | The Internet service name and instance number that was running on the client.
IIS | Server name | The name of the server on which the log file entry was generated.
IIS | Server IP address | The IP address of the server on which the log file entry was generated.
IIS | Time taken | The length of time that the action took, in milliseconds.
IIS | Client bytes sent | The number of bytes sent by the client.
IIS | Server bytes sent | The number of bytes sent by the server.
IIS | Service status code | A value of 200 indicates that the request was fulfilled successfully.
IIS | Windows status code | A value of 0 (zero) indicates that the request was fulfilled successfully.
IIS | Request type | The request verb.
IIS | Target of operation | The target of the verb, for example, Default.htm.
IIS | Parameters | The parameters that are passed to a scrip.
https://httpd.apache.org/docs/2.4/mod/mod_log_config.html
https://nginx.org/en/docs/http/ngx_http_log_module.html#log_format
https://docs.microsoft.com/en-us/windows/win32/http/w3c-logging
https://docs.microsoft.com/en-us/windows/win32/http/ncsa-logging
https://docs.microsoft.com/en-us/windows/win32/http/iis-logging

## 고려사항
구분 | 제품 | 용도 | 내용
오픈소스 | Vue | UI | 화면구성
| charjs | UI | 화면구성
| Nginx | Web/wsgi | AP서버
| Django Framework | AS | AP서버
| Postgresql | DB | 데이터베이스
| GeoIP | IP Country Mapper | GeoIP 란 MaxMind 에서 제공하는 국가별로 IP를 확인할 수 있는 오픈소스 라이브러리
Process | 내용
1 | 파일선택
2 | 포맷선택
3 | 시간선택
3 | 기본화면로딩
4 | 분석 - 테이블
5 | 분석 - 그래프
필터링
소팅(필드별)
시간 | 시/분/초
문자열 탐색

## 기능 - AWStats
Features
* Number of Visits, and number of Unique visitors.
* Visit duration and latest visits.
* Authenticated Users, and latest authenticated visits.
* Usage by Months, Days of week and Hours of the day (pages, hits, KB).
* Domains/countries (and regions, cities and ISP with Maxmind proprietary geo databases) of visitor's hosts (pages, hits, KB, 269 domains/countries detected).
* Hosts list, latest visits and unresolved IP addresses list.
* Most viewed, Entry and Exit pages.
* Most commonly requested File types.
* Web Compression statistics (for Apache servers using mod_gzip or mod_deflate modules).
* Visitor's Browsers (pages, hits, KB for each browser, each version, 123 browsers detected: Web, Wap, Streaming Media browsers..., around 482 with the "phone browsers" database).
* Visitor's Operating Systems (pages, hits, KB for each OS, 45 OS detected).
* Robots visits, including search engine crawlers (381 robots detected).
* Track Downloads such as PDFs, compressed files and others
* Search engines, Keywords and Phrases used to find your site (The 122 most famous search engines are detected like Yahoo, Google, Altavista, etc...)
* HTTP Errors (Page Not Found with latest referrer, ...).
* User defined reports based on url, url parameters, referrer (referer) fields extend AWStats' capabilities to provide even greater technical and marketing information.
* Number of times your site is added to Bookmarks / Favorites.
* Screen size (to capture this, some HTML tags must be added to a site's home page).
* Ratio of integrated Browser Support for: Java, Flash, Real G2 player, Quicktime reader, PDF reader, WMA reader (as above, requires insertion of HTML tags in site's home page).
* Cluster distribution for load balanced servers.
In addition, AWStats provides the following:
* Wide range of log formats. AWStats can analyze: Apache NCSA combined (XLF/ELF) or common (CLF) log files, Microsoft IIS log files (W3C), WebStar native log files and other web, proxy, wap, streaming media, ftp and mail server log files. See AWStats F.A.Q. for examples.
* Reports can be run from the operating system command line and from a web browser as a CGI (common gateway interface). In CGI mode, dynamic filter capabilities are available for many charts.
* Statistics update can be run from a web browser as well as scheduled for automatic processing.
* Unlimited log file size | 비기능
* Load balancing system split log files.
* Support 'nearly sorted' log files, even for entry and exit pages.
* Reverse DNS lookup before or during analysis; supports DNS cache files.
* Country detection from IP location (geoip) or domain name.
* Plugins for US/Canadian Regions, Cities and major countries regions, ISP and/or Organizations reports (require non free third product geoipregion, geoipcity, geoipisp and/or geoiporg database).
* WhoIS lookup links.
* Vast array of configurable options/filters and plugins supported.
* Modular design supports inclusion of addition features via plugins.
* Multi-named web sites supported (virtual servers, great for web-hosting providers).
* Cross Site Scripting Attacks protection. | 고급기능
* Reports available in many international languages. See AWStats F.A.Q. for full list. Users can provide files for additional languages not yet available.
* No need for esoteric perl libraries. AWStats works with all basic perl interpreters.
* Dynamic reports through a CGI interface.
* Static reports in one or framed HTML or XHTML pages; experimental PDF export through 3rd party "htmldoc" software.
* Customize look and color scheme to match your site design; with or without CSS (cascading style sheets).
* Help and HTML tooltips available in reports.
* Easy to use - all configuration directives are confined to one file for each site.
* Analysis database can be stored in XML format for easier use by external applications, like XSLT processing (one xslt transform example provided).
* A Webmin module is supplied.
* Absolutely free (even for web hosting providers); source code is included (GNU General Public License).
* Works on all platforms with Perl support.
* AWStats has a XML Portable Application Description.

## 기능 - apachelogviewer
Features |  |  | 기본 버전은 제약이 많음
Supports Common/Combined/Custom and additional Apache/nginx logs.
Supports NCSA/W3C IIS logs
Handles multiple logs
Supports compressed .gz logs
Supports IPv4 & IPv6
Split logs functionality by size/date
Monitor logs in realtime (with automatic refresh) both local and remove via FTP/SFTP
Highlight requests by status code
Converts IP & IPv6 to Country
Search by any combination of Request, Date, IP, Referrer and UserAgent
Filter by any combination of Status/IP Address, GET, HEAD, POST Requests, Date, Referrer or User-agent
Export to text file (txt), comma separated value (csv), log file or html
Statistics
Total Hits (by days)
Status Codes (by days)
Bandwidth (by days)
Top IP Addresses *
Top Requests *
Top Countries *
Top 404 URLs *
Top Referers *
Top User Agents *
Bot IP Addresses *
Country IP Addresses *
File Types *
Referrer Visits *
Referrer Hotlinking *
Search Terms *
Visits Count *
Report
Hits Each Day | Column | Hits per day
Visits by IP | Column | Hits from a particular IP Address
Visits by Referrer | Column | Hits originating from a particular referrer
Visits by Request | Column | Hits originating for a particular request
Visits from Country | Column | Hits originating from a particular country
Visits by UserAgent | Column | Hits originating from a particular user agent
Visits by User | Column | Hits originating from a particular user
Unique Hits | Column | Unique hits per day
Unique Hits (Bots Excluded) | Column | Unique hits per day but excluding bots
Unique Hits (start date) | Column | Unique hits per day but only from a particular date onwards
Visits by IP | Column | Unique hits from a particular IP Address
Visits by Referrer | Column | Unique hits from a particular referrer
Visits by Request | Column | Unique hits for a particular request
Visits from Country | Column | Unique hits from a particular country
Visits by UserAgent | Column | Unique hits from a particular user agent
Visits by IP & Request | Column | Unique hits from a particular IP Address for a particular request
Visits by Request & UserAgent | Column | Unique hits from a particular request and a particular user agent
Visits by Country & Request | Column | Unique hits from a particular country and for a particular request
Visits by User | Column | Unique hits from a particular user
Any | Column | Hits per Hour for a particular day
From IP | Column | Hits per Hour from a particular IP Address
From User | Column | Hits from a particular user
For Request | Column | Hits per Hour for a particular request in a particular day
For Request (substring) | Column | Similar as above but takes part of the request
Hits each Month | Column | Number of hits in a particular month
Hits each Week | Column | Number of hits aggregated per week
Bot Hits | Column | Hits from Bots
IPv6 per Day | Column | Hits from an IP version 6 address
IPv6 per Day (Unique) | Column | Unique hits from an IP version 6 address
Search Visits | Column | Shows request that came from search visits
Spider Visits | Column | Shows number of visits from spider bots
Users per Day | Column | Total users visited per day
Users and Average TimeTaken | Column | Users visited and the average time taken for each request
Requests & Average TimeTaken
Top IP Hits per Day | Stacked Column | Top IP Addresses per day
Top Error IP Hits per Day | Stacked Column | Top IP Addresses resulting in 4xx status codes per day
IP Hits per Day | Stacked Column | Particular IP Addresses requesting requests per day
Top Requests per Day | Stacked Column | Shows which requests are the most requested (popular)
Top Error Requests per Day | Stacked Column | Shows which requests result in 4xx status codes
Requests per Day | Stacked Column | Shows number of fetches for a set of requests
Search Terms per Day | Stacked Column | Shows terms that have been used in search terms per day
Status Codes per Day | Stacked Column | Shows number of status codes per day
Bandwidth by Type | Stacked Column | Shows bandwidth count for particular file types on a per day basis
File Types per Day | Stacked Column | Shows total hits for specific file types on specific days
Referrers per Day | Stacked Column | Shows refererrs on a per day basis
User Agent | Pie | Hits from a particular User Agent
Desktop Browser (hits) | Pie | Hits originating from desktop browsers
Mobile Browser (hits) | Pie | Hits originating from mobile browsers
By Request (hits) | Pie | Hits from a particular browser requesting a specific request
By Country (hits) | Pie | Hits from a particular browser originating for a specific country
Visits by Country | Pie | Hits and the originating country
Visits by Country (Reduced) | Pie | Similar as Visits by Country but only displays a selection of the top countries
Visits by Region | Pie | Hits and the originating region - North America, South America, Europe, Africa, Asia & Pacific
Desktop Browsers | Pie | Unique hits originating from the traditional desktop browsers
Mobile Browsers | Pie | Unique hits originating from mobile browsers
Desktop vs Mobile | Pie | Unique hits showing total traditional desktop vs mobile browser
By Request | Pie | Unique hits from a particular browser requesting a specific request
By Country | Pie | Unique hits from a particular browser originating for a specific country
Request Analysis | Pie | Shows which parts of the website were accessed and by what percentage.
Traffic Sources | Pie | Shows referrer source i.e. Direct, Referrer or Search Engine
Status Code | Pie | Shows percentage of status codes
Operating System | Pie | Shows percentage of each operating system used to visit
Geo Country Visits | Map | Shows graphical map with intensity of visits
Geo Country Visits (start date) | Map | Shows graphical map with intensity of visits but after a specific date
Bandwidth | Line | Shows total bandwidth used to serve hits

## 기능 - goaccess
Features - Panel로 구분
General Statistics
number of valid and invalid requests
time taken to analyze the data set, unique visitors, requested files, static files (CSS, ICO, JPG, etc) HTTP referrers, 404s
size of the parsed log file and bandwidth con‐ sumption.
Unique visitors:
hits, unique visitors and cumulative bandwidth per date
HTTP requests containing the same IP, the same date
the same user agent are considered a unique visitor
| date specificity can be set to the hour | 특정 시간레벨로 정렬
Requested files
Requested static files
most highly requested (non-static/static) files
hits, unique visitors, and percentage, along with the cumulative bandwidth, protocol, and the request method used
static files such as: JPG, CSS, SWF, JS, GIF, and PNG file types
404 or Not Found | its data contains all pages
Hosts | detailed information on the hosts themselves.
country of origin and city
Operating Systems | operating system the host used when it hit the server
Browsers | browser the host used when it hit the server
Visit Times | hour specificity can be set to the tenth of a minute level using |  | 특정 시간레벨로 정렬
Virtual Hosts | This panel will display all the different virtual hosts parsed from the access log
Referrers URLs | the host in question accessed the site via another resource, or was linked/diverted to you from another host, the URL they were referred from will be provided
Referring Sites | 상동
Keyphrases
Geo Location | Determines where an IP address is geographically located
HTTP Status Codes | The values of the numeric status code to HTTP request
Remote User (HTTP authentication) | MIS에 일반적이지 않음